Project Design Phase-II Sprint Planning Logic HematoVision: Advanced Blood Cell Classification Using Transfer Learning Team ID: TSK841298 ¦ Date: 27 February 2026

Key Definitions

| Sprint | A fixed time-period (2 weeks) in which the team completes a set of planned tasks. |
| --- | --- |
| Epic | A large feature or goal too big for one sprint — broken into smaller user stories. |
| Story | A small, user-focused task that is part of an Epic and completable within one sprint. |
| Story Point | A Fibonacci number representing the relative effort required to complete a story. |
| Velocity | Average story points completed per sprint. Used to predict future sprint capacity. |

Story Point Scale (Fibonacci: 1, 2, 3, 5, 8)

| Story Points | Effort Level |
| --- | --- |
| 1 | Very Easy — quick sub-task, no unknowns (e.g. load a CSV file) |
| 2 | Easy — straightforward task with minor complexity (e.g. data split) |
| 3 | Moderate — requires design thinking or external integration (e.g. augmentation pipeline) |
| 5 | Difficult — significant effort, multiple components or uncertainty (e.g. CNN fine-tuning) |
| 8 | Very Difficult — large scope, high complexity or research required |

Sprint 1 (Weeks 1-2) — Data Collection & Preparation

Epics: Epic-1 (Data Collection)  |  Epic-2 (Data Preparation & Preprocessing)

| USN | Epic | User Story / Task | Story Points |  |
| --- | --- | --- | --- | --- |
| USN-1 | Epic-1: Data Collection | As a data engineer, I can collect and curate a labelled blood cell image dataset (BCCD) with RBC, WBC, Platelet and Blast classes for model training. | 3 |  |
| USN-2 | Epic-1: Data Collection | As a data engineer, I can split the dataset into training (70%), validation (15%) and test (15%) sets and store them in the file system. | 2 |  |
| USN-3 | Epic-1: Data Collection | As a data engineer, I can load and verify image metadata (labels, file paths, class distribution) and log any corrupted or missing files. | 2 |  |
| USN-4 | Epic-2: Data Preparation | As an ML engineer, I can resize all blood smear images to 224x224 pixels and normalise pixel values to [0,1] range for CNN input compatibility. | 3 |  |
| USN-5 | Epic-2: Data Preparation | As an ML engineer, I can apply data augmentation (rotation, flip, zoom, brightness) to the training set to improve model generalisation and handle class imbalance. | 3 |  |
| USN-6 | Epic-2: Data Preparation | As an ML engineer, I can implement an automated image quality validation pipeline to flag and exclude blurry or under-exposed blood smear images. | 3 |  |
| Total Story Points — Sprint 1: |  |  | 16 |  |

Sprint 2 (Weeks 3-4) — Model Development & Web Application

Epics: Epic-3 (CNN Model Development)  |  Epic-4 (Web Application & API)

| USN | Epic | User Story / Task | Story Points |  |
| --- | --- | --- | --- | --- |
| USN-7 | Epic-3: Model Development | As an ML engineer, I can fine-tune a pre-trained ResNet50 CNN on the BCCD dataset with transfer learning to classify blood cell types. | 5 |  |
| USN-8 | Epic-3: Model Development | As an ML engineer, I can evaluate model performance using accuracy, precision, recall and F1-score, achieving >= 90% accuracy on the test set. | 3 |  |
| USN-9 | Epic-3: Model Development | As an ML engineer, I can implement Grad-CAM explainability to generate a heatmap overlay showing which regions of the blood smear the CNN focused on. | 3 |  |
| USN-10 | Epic-4: Web Application | As a developer, I can build a Flask REST API backend with endpoints for image upload, CNN inference, result retrieval and report download. | 5 |  |
| USN-11 | Epic-4: Web Application | As a developer, I can build a React.js frontend with image upload UI, result display (cell type, confidence score, Grad-CAM overlay) and PDF download button. | 5 |  |
| USN-12 | Epic-4: Web Application | As a developer, I can implement user authentication (JWT) and role-based access control (Clinician / Pathologist / Admin) on the web portal. | 3 |  |
| Total Story Points — Sprint 2: |  |  | 24 |  |

Sprint 3 (Weeks 5-6) — Database, Storage & Deployment

Epics: Epic-5 (Database & Cloud Storage)  |  Epic-6 (Deployment & Testing)

| USN | Epic | User Story / Task | Story Points |  |
| --- | --- | --- | --- | --- |
| USN-13 | Epic-5: Database & Storage | As a developer, I can design and implement a PostgreSQL schema for storing classification results, user data, case history and audit logs. | 3 |  |
| USN-14 | Epic-5: Database & Storage | As a developer, I can integrate IBM Cloud Object Storage / AWS S3 for encrypted storage of uploaded blood smear images and generated reports. | 3 |  |
| USN-15 | Epic-5: Database & Storage | As a developer, I can implement a PDF/CSV report generation engine (ReportLab) including cell type, confidence, Grad-CAM image and timestamp. | 3 |  |
| USN-16 | Epic-6: Deployment | As a DevOps engineer, I can containerise the Flask API and CNN inference service using Docker and deploy to Kubernetes (IBM IKS / AWS EKS). | 5 |  |
| USN-17 | Epic-6: Deployment | As a DevOps engineer, I can configure Nginx as a reverse proxy / load balancer, set up Redis caching and Celery async task queue for batch inference. | 3 |  |
| USN-18 | Epic-6: Deployment | As a QA engineer, I can execute end-to-end integration tests, load tests (100 concurrent users) and security vulnerability scans before go-live. | 3 |  |
| Total Story Points — Sprint 3: |  |  | 20 |  |

Velocity Summary

| Sprint | Sprint 1 | Sprint 2 | Sprint 3 | Total SP | Velocity |
| --- | --- | --- | --- | --- | --- |
| Story Points | 16 | 24 | 20 | 60 | 60 / 3 = 20 SP/Sprint |

Velocity Calculation Total Story Points = 16 + 24 + 20 = 60 Number of Sprints = 3 Velocity = Total Story Points / Number of Sprints = 60 / 3 = 20 Team Velocity = 20 Story Points per Sprint